## Sheet1
WBS Code | Level | Task Name | Description | Estimated Effort (Engineer-Months) | Dependencies | Notes and Key Deliverables
1 | 1 | Project Initiation and Planning | Overall project setup, scoping, and PoC | 3 | - | -
1.1 | 2 | Define requirements and scope | Document must-have vs nice-to-have features compared to Splink | 0.8 | - | Requirements traceability matrix
1.2 | 2 | Conduct gap analysis against current systems | Map current identity resolution pipeline vs Splink capabilities | 0.7 | 1.1 | Gap report + prioritized backlog
1.3 | 2 | Develop proof-of-concept (PoC) | Build minimal blocking + simple comparison + basic EM on sample data | 1.2 | 1.2 | Working PoC notebook + 5–10 min demo
1.4 | 2 | Assemble team and set up dev environment | Spark cluster, repo, CI skeleton, coding standards | 0.3 | 1.1 | Team onboarded, repo created, basic pipeline runs
2 | 1 | Core Module Development | Implementation of the main engine pieces | 24 | 1.0 (PoC learnings) | -
2.1 | 2 | Data Ingestion and Preparation |  | 4 | - | -
2.1.1 | 3 | Data loading connectors (SQL, CSV, Parquet, graph export) | Support for main customer data sources | 1.2 | - | Connectors tested with real schema samples
2.1.2 | 3 | Schema mapping & standardization | Handle varying column names/types across sources | 1 | 2.1.1 | Standardized schema definition + mapping config
2.1.3 | 3 | Data cleaning & missing value strategies | Standard pre-processing steps used in linkage | 0.8 | 2.1.2 | Cleaning rules library + unit tests
2.1.4 | 3 | Partition and sampling utilities | For dev & testing on subsets | 0.5 | 2.1.3 | Sampling functions that preserve entity distribution
2.2 | 2 | Blocking Engine |  | 5 | - | -
2.2.1 | 3 | Blocking rule definition DSL (SQL-like or YAML) | User-configurable blocking predicates | 1.5 | - | DSL parser + validator
2.2.2 | 3 | Blocking key generation & indexing | Create candidate pairs efficiently in Spark | 1.8 | 2.2.1 | Efficient wide tables or exploded-pair representation
2.2.3 | 3 | Blocking performance diagnostics & optimization | Tools to measure reduction ratio & skew | 1 | 2.2.2 | Blocking diagnostics report template
2.2.4 | 3 | Support for multi-pass or hierarchical blocking | Allow combining different blocking strategies | 0.7 | 2.2.3 | Example multi-pass config
2.3 | 2 | Comparison Library |  | 5 | - | -
2.3.1 | 3 | Core similarity functions library | String (Levenshtein, Jaro-Winkler, token), numeric, date, exact | 1.8 | - | Comprehensive function registry
2.3.2 | 3 | Comparison level definition & configuration system | Thresholds, weights, m/u values per level | 1.5 | 2.3.1 | Config schema + validation
2.3.3 | 3 | Custom comparison functions | Allow domain-specific logic | 0.9 | 2.3.2 | Extension point + example implementations
2.3.4 | 3 | Comparison vector materialization | Spark job that creates feature vectors for candidate pairs | 0.8 | 2.3.2 | Efficient wide comparison table
2.4 | 2 | Probabilistic Modeling (EM Estimator) |  | 6 | - | -
2.4.1 | 3 | Fellegi-Sunter model implementation | Core probability math (m, u, lambda) | 1.5 | 2.3.4 | Model equations + unit tests
2.4.2 | 3 | Expectation-Maximization algorithm | Unsupervised parameter estimation | 2.2 | 2.4.1 | Convergence diagnostics & early stopping
2.4.3 | 3 | Semi-supervised or labeled data mode | Allow small labeled set to improve estimates | 1 | 2.4.2 | Label incorporation logic
2.4.4 | 3 | Parameter smoothing & regularization | Handle rare comparisons, avoid extremes | 0.8 | 2.4.2 | Smoothing options + defaults
2.4.5 | 3 | Model diagnostics & goodness-of-fit | Charts: match weights, u-values, ROC-like curves | 0.5 | 2.4.4 | Diagnostic notebook templates
2.5 | 2 | Prediction and Clustering |  | 4 | - | -
2.5.1 | 3 | Match probability scoring & thresholding | Apply model to produce final match scores | 1.2 | 2.4.5 | Scoring job + threshold selection helpers
2.5.2 | 3 | Entity resolution and clustering | Connected components or union-find on predicted matches | 1.5 | 2.5.1 | Cluster ID assignment logic
2.5.3 | 3 | Canonical record selection, golden record rules | Basic survivorship rules per cluster | 0.8 | 2.5.2 | Rules engine + config
2.5.4 | 3 | Export formats (CSV, graph nodes and edges, JSON) | Deliverable formats for downstream systems | 0.5 | 2.5.3 | Multiple export writers
3 | 1 | User Tools and Integration |  | 9 | 2 | -
3.1 | 2 | Visualization and Configuration Interface |  | 4 | - | -
3.1.1 | 3 | Interactive model tuning dashboard (Jupyter) | Match weights, u-values, blocking summary | 2 | - | Tunable charts similar to Splink
3.1.2 | 3 | Model configuration YAML validator | Human-readable settings file | 1.2 | 3.1.1 | Schema validation + examples
3.1.3 | 3 | Linkage result explorer | Drill-down into clusters & comparison vectors | 0.8 | 3.1.1 | Result browser prototype
3.2 | 2 | System Integration |  | 3 | - | -
3.2.1 | 3 | Neo4j graph database write connectors | Merge nodes and create relationships from resolved clusters | 1.2 | 2.5.4 | Graph write API
3.2.2 | 3 | Orchestration hooks | Standardized task templates | 1 | 3.2.1 | DAG fragment examples
3.2.3 | 3 | Monitoring & alerting integration | Prometheus metrics or similar | 0.8 | 3.2.2 | Basic observability
3.3 | 2 | Security and Compliance |  | 2 | - | -
3.3.1 | 3 | Data anonymization & tokenization | PII masking during linkage | 1 | - | Anonymization layer
3.3.2 | 3 | Audit logging & lineage tracking | Track which records map to which cluster | 1 | 3.3.1 | Audit trail schema
4 | 1 | Testing and Validation |  | 6 | 2.0 + 3.0 | -
4.1 | 2 | Unit & Integration Testing |  | 3 | - | Pytest suite
4.1.1 | 3 | Unit tests – individual functions & classes | 80%+ coverage target on core logic | 1.5 | - | -
4.1.2 | 3 | Integration tests – end-to-end linkage jobs | Small synthetic datasets | 1.5 | 4.1.1 | -
4.2 | 2 | Performance Benchmarking |  | 2 | - | -
4.2.1 | 2 | Run benchmarks vs open-source Splink | Wall-clock time, memory, accuracy | 1.2 | - | Benchmark report
4.2.2 | 2 | Scale tests from 100K to 10M to 100M | Identify scaling bottlenecks | 0.8 | 4.2.1 | Scaling characterization
4.3 | 2 | User Acceptance Testing & internal demos | Business & data team feedback loops | 1 | - | Demo sessions + feedback log
5 | 1 | Deployment and Documentation |  | 6 | 4 | -
5.1 | 2 | Production Deployment |  | 2 | - | -
5.1.1 | 3 | CICD pipeline | Automated releases | 0.8 | - | -
5.1.2 | 3 | Production environment setup & monitoring |  | 1.2 | 5.1.1 | -
5.2 | 2 | Documentation and Training |  | 2 | - | -
5.2.1 | 3 | API reference & user guide | How to configure and run | 1 | - | Markdown + MkDocs
5.2.2 | 3 | Example notebooks & tutorials | Common use cases | 1 | 5.2.1 | -
5.3 | 2 | Post-Launch Support Planning | Maintenance roadmap & bug triage process | 2 | - | Sprint planning template + on-call rota
4